## Register
Project Name & Number |  | #REF! | #REF! | [7 empty] | Contractor:
CRF no | Requested By | Date Issued | Description of Change | Forecast Budget | Contingency | Anticpated Value of Contingency Draw | Revised Contingency | Status (Open / Closed) | Value (Agreed) | Accepted | Rejected | Response Issued to Relevant Party | Employer Instruction Number | Comments | Variation
|  |  | Business Case Budget sign off | 15800000 | 1000000
1 | UoL Matt Flint | 2017-06-13 | Change lead design consultant and multi-disciplinary design team, from BDP to SHE, comprising architect, mechanical and electrical services engineer, civil and structural engineering services. | 15800000 | 1000000 | 91855 | 1000000 | Closed | 91855 | Yes | No | Yes | n/a | SEH services to commence 12 June following issue of Purchase order.
2 | Zoe Radnor | 2017-07-21 | Design/scope creep/adjustment of 3 key areas that the client felt did NOT meet expectations at end of stage 3; 1) lecture theatre arrangement and increase capacity to c. 180-200 2) Improve connectivity within central ground floor communal area between main entrance of main house and lecture theatre 3) review stable block allocation of use and finish. | 15800000 | 1000000 | 145000 | 1000000 | Closed | 145000 | Yes | No | Yes | n/a | SEH reviewed initial options with client team during stage 3 due-diligence period, final options to be presented to QS for costing and client for final review.
3 | Zoe Radnor | 2017-07-19 | Mechanical cooling to currently naturally ventilated areas that may over heat during high temperature summer months. Areas may include lecture theatre, main house and upper floors of new build. | 15800000 | 1000000 | 120000 | 1000000 | Closed | 120000 | Yes | No | Yes | n/a | In-lieu of no BDP thermal model, design in process of establishing areas of 'high temperature' and to propose potential solutions, inc' cause/effect of implementing mechanical cooling (cost etc.).
4 | UoL John Pointon | 2018-04-06 | Utilisation of the project contingency to cover the overspend associated with the appointment of Henry Boots. | 15800000 | 1000000 | 180425.5 | 819574.5 | Closed | 180425.5 | Yes | No | Yes | n/a | Process to appoint Henry Boots commenced in order to meet construction programme.
5 | Nicky Randall | 2018-04-18 | Change the existing kitchen cupboard door units and associated changes. | 15800000 | 819574.5 | 0 | 819574.5 | Closed | 24000 | No | Yes | Yes | n/a | Quotation for the change being priced by Westminster Building Services, project team cost estimated at £24,000. Decided not to pursue at board meeting during April 2018.
6 | Matthew Flint | 2018-04-18 | Late design change means that the Mallard doors may not be installed prior to handover of the internal spaces - Proposal is to install the doors prior to occupation of the building. The lead-in of the doors tbc by the contractor following instruction to proceed, lead-in estimated at 8 weeks by Contractor. | 15800000 | 819574.5 | 0 | 819574.5 | Closed | 22471.2 | No | Yes | Yes | n/a | Firm priced received from the contractor to replace the external doors to Mallard and Kingfisher at £22,471. Decided not to pursue at board meeting during April 2018. Other options being pusrued.
7 | Nicky Randall | 2018-04-18 | Design/scope creep/adjustment. Additional works include replacing carpets, additional seating, signage, AV equipment and increased provisions behind the reception desk to install full height cupboards. | 15800000 | 819574.5 | 13461 | 806113.5 | Closed | Discussions On-going | Yes | No | Yes | n/a | Quotation for the change being priced by Westminster Building Services, project team cost estimate submitted with the change request.
8 | Nicky Randall | 2018-04-18 | Full scale carpet replacement to the Mallard, Heron, Kingfisher and PGTC corridors. | 15800000 | 806113.5 | 0 | 806113.5 | Closed | N/A | No | Yes | Yes | n/a | Quotation for the change being priced by Westminster Building Services, project team cost estimate submitted with the change request. Decided not to pursue at board meeting during April 2018. Other options being pusrued.
9 | Matthew Flint | 2018-05-17 | Statutory provision for the installation of fire breaks and access panels to the PGTC roof space. | 15800000 | 806113.5 | #REF! | #REF! | Closed | 3648 | Yes | No | Yes | n/a | Quotation for the works issued by Westminster Building Services. Cost currently being assessed by MDA.
10 | Matthew Flint | 2018-05-17 | The increase in costs is due to the reconciliation of the approporaite fees as consultants hadn’t changed from the original £6mill budget. There have been additional minor surveys undertaken and the insurance provisions had not been allowed for within original budget. | 15800000 | #REF! | #REF! | #REF! | Closed | #REF! | Yes | No | Yes | n/a
11 | Matthew Flint | 2018-05-18 | The revised change control relates to the clean and rub down, paint Undercoat and Gloss finish to the External doors to the Mallard and Kingfisher buildings. The change control also allows for the installations of the Salto Access control system to both doors as detailed within Westminster Building's original quotation for the works. | 15800000 | #REF! | #REF! | #REF! | Closed | #REF! | Yes | No | Yes | n/a
12 | Henry Boot/ SE-H | 2018-06-15 | Post-Tender variation nr 2 was for a revised roof finish to the PGTC (over the new Kitchen and Courtyard areas). The existing roof finish over the whole of the PGTC is a bitumen system and the variation requested a bitumen system to the kitchen/courtyard, as the tender docs requested a single-ply system. | 15800000 | #REF! | 0 | #REF! | Closed | #REF! | No |  | Yes |  | Change control rejected. UoL decision to proceed with the tendered roof build-up (single-ply membrane).
13 | UoL | 2018-06-22 | #REF! | 15800000 | #REF! | #REF! | #REF! | Open | Under MDA Assessment | TBC |  | TBC
|  |  | Total Value of CCRF's Accepted to Date |  |  | #REF! |  | Total Cost | #REF!
|  |  | Contract Value |  |  | 15800000 |  | % of Cont'y | #REF!
|  |  | Contingency Value |  |  | 1000000
|  |  | Current Contingency Value |  |  | #REF!

## 01_Example
University of Leicester
PRE-CONSTRUCTION - CHANGE CONTROL REQUEST FORM (CCRF)
| Project Nr: | N16.046 | [5 empty] | Project Name: |  | Brookfield School of Business
Consult Change Order Number | Date Raised | [7 empty] | Sequential Number ... * |  | 01 | Rev...* | 1
| Initial Action Required By |  | UoL Development | [5 empty] | (*Controlled by PM)
Change Order raised by (name) | Change Request Raised By (Name)
| Change Title |  | Lead Consultant & Multi-Disciplinary Consultant Change
Date Decision Required
Details of proposed change
Change lead design consultant and multi-disciplinary design team, from BDP to SHE, comprising architect, mechanical and electrical services engineer, civil and structural engineering services.
Reason for change
Concerns in regard performance and value for money following completion of RIBA Stage 2 -3 and application for considerable professional fee uplift though stages 4-7 that form a digression from the basis of appointment (UoL Framework).
Source of change (attach as appropriate)
Unable to negotiate an appropriate stage 4-7 fee or obtain suitable reassurances from BDP in regard to performance improvement.
Consultants Affected
BDP - Exiting design team. SHE - Entering design team.
Design Information Affected (Drawings, Schedules, Specifications)
RIBA Stage 3 information; however considered minimal due to stage being completed in its majority.
| Cost Implications: | [5 empty] | Additional Notes:
| Construction: | [7 empty] | Consultant (Fee's):
| Client Team Estimated Cost |  |  | £ |  | n/a |  |  | Client Team Estimated Cost |  | £ | n/a
| Contractor Estimated Cost |  |  | £ |  | n/a |  |  | Consultant Estimated Cost |  | £ | 91855
| Agreed Cost |  |  | £ |  | n/a |  |  | Agreed Cost |  | £ | 91855
Change impact
| Current Budget |  |  | £ |  | 15800000 |  |  | Current Contingency |  | £ | 1000000
| Forecast Budget |  |  | £ |  | 15800000 |  |  | Forecast Contingency |  | £ | 1000000
Programme Implications
| Contract Administrator's Estimated Effect On Programme | [6 empty] | 12 weeks |  | Working Days +/-
| Contractor Estimated Effect On Programme | [6 empty] | n/a |  | Working Days +/-
| Agreed Estimated Effect On Programme | [6 empty] | 12 weeks |  | Working Days +/-
Other Comments
| Please indicate your Approval / Rejection plus any comments: | [7 empty] | Approved / Rejected
Comments:
Approval Signature [UoL Client Representative]
Distribution
[5 empty] | (Tick as appropriate) | [6 empty] | (Tick as appropriate)
| [Client - UoL Internal PM] |  | X | [5 empty] | [UoL Estates Representative - UoL] |  | X
| [Client - UoL End-User] |  | X | [5 empty] | [M&E and C&S Engineer] |  | X
| [Architect] |  | X | [5 empty] | [Contractor]
| [Quantity Surveyor] |  | X | [5 empty] | [Principle Designer] |  | X