## 01
Project Number |  | Project Title
Date Raised |  |  | Sequential Number
Initial Action Required By |  |  | Controlled By
Change Request Raised by
Change Title
Date Decision Required
Details of Proposed Change
Reason for change
Source of Change (attach as appropriate)
Consultants Affected
Design Information Affected (Drawings, Schedules, Specifications)
Cost Implications |  | Additional Notes
Construction |  |  | Consultant (Fee's):
Client Team Estimated Cost |  |  | Client Team Estimated Cost
Contractor Estimated Cost |  |  | Consultant Estimated Cost
Agreed Cost |  |  | Agreed Cost
Change impact
Current Budget |  |  | Current Contingency
Forecast Budget |  |  | Forecast Contingency
Programme Implications
Contract Administrator's Estimated Effect On Programme |  |  |  | Working Days +/-
Contractor Estimated Effect On Programme |  |  |  | Working Days +/-
Agreed Estimated Effect On Programme |  |  |  | Working Days +/-
Other Comments
Please indicate your Approval / Rejection plus any comments: |  | Approved / Rejected
Comments:
Approval Signature [UoL Client Representative]
Distribution | (Tick as appropriate) |  |  | (Tick as appropriate)
[Client - UoL Internal PM] |  |  | [UoL ECS Representative]
[Client - UoL End-User] |  |  | [M&E and C&S Engineer]
[Architect] |  |  | [Contractor]
[Quantity Surveyor] |  |  | [Principle Designer]