## Dashboard
July 2018 - Report #00
2017
A |  | Start | End | + / - | MAY |  | JUNE | JULY | AUG |  |  | SEPT | OCT | NOV |  | DEC
| Design Development to Tender | [15 empty] | A | Summary of key points |  |  | A | G | G | A | G | A | A | G
G | RIBA Stage 1 - Preparation & Brief
G | RIBA Stage 2 - Concept Design
G | Agree Procurement Strategy
G | EWC Approval to Proceed to RIBA Stage 3
G | RIBA Stage 3 - Developed Design & Approval to Stage 4
G
A
A | RIBA Stage 4 - Technical Design
A
A | Approval of Stage 4 - Proceed to Tender
Planning (Local Planning Authority)
A
A
A
A
A
A
Principal Contractor Procurement
G | [17 empty] | Gate 0 | Status | Gate 1-2 | [8 empty] | Status
G | [17 empty] | Desktop H&S Review |  | Additional F10
G | [17 empty] | Headline Risk Register |  | Surveys complete
A | [17 empty] | Review of existing building information |  | H&S File Structure agreed
A | [17 empty] | H&S Survey Schedule |  | Construction Phase Plan approved
A | [17 empty] | Gate 1 | Status | On Site | [8 empty] | Status
| De-Cant Requirements | [16 empty] | Initial F10 Submitted |  | Monthly H&S site inspections complete
G | [17 empty] | PCI complete |  | H&S Insp. Corrective Actions closed out
G | [17 empty] | Design H&S Risk Workshop |  | No of Lost Time Acc/Inc in period
G | [17 empty] | Detailed H&S Risk Register |  | Acc/Inc Investigations completed
Construction (inc' 4 wks Mobilisation)
R | Construction (inc' 4 wks Mobilisation)
A | Available and Ready for Full Use / Occupation | [15 empty] | A
A
|  | Budget (Date) | Forecast FA | Budget Variance | [12 empty] | A
G | Cost Summary |  |  |  | G | Change Control: | [10 empty] | G
G | Construction - Enabling Works (Westminster Building Services Contract) |  |  | 0 | Issued to date |  |  | Open |  |  |  | Closed Out |  | New in Period |  |  | G
| Construction - Main Contract (Based on confirmed Henry Boots Tender Figure) | [15 empty] | G
G | VE Process Being Undertaken With Design Team and Henry Boots |  |  |  | 0 |  |  | 0 |  |  |  | #DIV/0! |  | 0 |  |  | G
CRF/ Variations Implemented
G | Nett Construction | 0 | 0 | 0 | G | Instruction / Compensation Events:
G | Professional Fees & Surveys |  |  | 0 | Issued to date |  |  | Open |  |  |  | Closed Out |  | New in Period |  |  | A | Principal design issues developed / require close-out / user forum group input:
G | General Loose Furniture Allowance (FF&E) |  |  | 0 | [12 empty] | A
G | Audio Visual (AV) |  |  | 0 | 0 |  |  | 0 |  |  |  | 0% |  | 0 |  |  | G
G | Allowance for IT Equipment & WiFi |  |  | 0 | [12 empty] | G
G | Allowance for IT from Main Campus |  |  | 0 | [12 empty] | G
G | Decant Costs (inc' in Loose Furniture FF&E) |  |  | 0 | [12 empty] | G
G | Asbestos Removal |  |  | 0 | [12 empty] | G
G | Enabling Works / Boiler Replacement |  |  | 0 | G | Design Stage RIBA: |  |  |  | G | Approval Gateway |  |  |  | Date |  | A
G | Security |  |  | 0 | RIBA |  |  | 1 | [8 empty] | A
G | Contingency (10% of sub-total of items above) |  |  | 0 | [12 empty] | G
G | Inflation Allowance |  |  | 0 |  |  |  | 2 | [8 empty] | G
0
G | Project Budget Totals (exc' VAT) | 0 | 0 | 0 |  |  |  | 3 | [10 empty] | £
G | VAT @ 20% |  |  | 0 | [12 empty] | 1 |  |  |  |  | Project Boards
G | VAT Recovery (TBC by Advisor) |  |  | 0 | [12 empty] | 2 |  |  |  |  | Project Boards
G | Project / Budget Totals (inc' VAT) | 0 | 0 | 0 | [12 empty] | 3 |  |  |  |  | Project Boards
|  | BUDGET +/- | #DIV/0! | [13 empty] | 4
[17 empty] | 5 |  |  |  |  | Project Progress & DT Meetings
|  | CONTING'Y 'v' FFA | #DIV/0! | [13 empty] | 6 |  |  |  |  | Project Progress & DT Meetings
[17 empty] | 7 |  |  |  |  | Project Progress & DT Meetings
R | Items in RED – the requirements are either not in place or are in place but the item poses an immediate risk to the successful completion of the project. Finance = <+10% over budget estimate. Programme = delay that impacts/defers occupation of the asset, forcing 3rd party impact/input. H&S = Significant risk to project team and/or occupants. | [15 empty] | 8 |  |  |  |  | Project Progress & DT Meetings
A | Items in AMBER – the requirements are not in place and still require completing or are in place but there is risk to the project surrounding the item. Finance = >+5% over budget estimate. Programme = delay that has the potential to delay task/activity however NOT operation and use of the asset. H&S = issue that has been recognised but is a manageable risk. | [15 empty] | 9 |  |  |  |  | Stage 4 Risk Workshop
G | Items in GREEN – the requirements are in place and currently there is no risk to the project. Finance = within budget and contingency threshold. Programme = on programme to deliver asset by prescribed deadline. H&S = No Issues. | [15 empty] | 10
TASK (Baseline Master Prog Rev01)
)
BUDGET PERFORMANCE
PROJECT SCOPE
PROJECT COMMENTARY
TOP 10 PROJECT RISKS
FORTHCOMING MEETINGS
Contract
Programme
Budget
Key Actions
Design
Approvals
Risk
Summary
PROGRAMME PERFORMANCEG
CONTRACT ADMINISTRATION
PROJECT DECISIONS & KEY ACTIONS
DESIGN UPDATE
COST STATUS ('v' Budget)
CURRENT STATUS - GATEWAY APPROVALS
HEALTH & SAFETY PROGRESS UPDATE

## Data
Change Control
Change Control
< 74.9%
Issued to Date |  | input |  | 75.0 - 89.9%
Closed Out |  | input |  | > 90.0%
Open |  | Auto | #DIV/0!
New in Period |  | input
Variations / Instructions / CE's
Compensation Events / Instructions
< 74.9%
Issued to Date |  | input |  | 75.0 - 89.9%
Closed Out |  | input |  | > 90.0%
Open |  | input | #DIV/0!
New in Period |  | input
Contingency
Budget Allowance |  | Auto |  | < 4.9%
Current FA Build |  | Auto |  | 5.0 - 9.9%
Current FA Allowance |  | Auto |  | > 10.0%
% against forecast FA Build | #DIV/0! | Auto
% against current risk register | 0 | input
Project Status Report
All actions completed satisfactorily and evidence is available
Not all actions are complete to progress to next Gate. Outstanding actions have planned date.
There are overdue actions that must be completed to allow the project to progress.