## Meeting Sched
Last Updated: | 2020-11-30
Meeting | Frequency | Purpose | Date | Time | Location | Chair | Form of Record | Minimum Reporting Documents (Issued to Chair 3 days in advance of Meeting) | Author | Attendees
Project Board | Monthly | High Level Governance Forum - Review overall status of the project; strategy, business case, gateway approvals, performance (time/cost/quality), issues/risks, success criteria, escalation. |  |  |  | (As designated) | Minutes and Task Log | Project Manager Dashboard (additiional accompanying documents as required) | Internal Project Manager
Project Progress Meeting | Monthly (minimum) | Review overall project progress; design development, programme, procurement, risk, quality, logistics and cost. |  |  |  | Client - Internal Project Manager John Pointon | Minutes and Task Log |  |  | Required
UoL Internal PM - John Pointon
Lead Design (Inc CDM) Representative - Moss
Lead Client Representative -
UoL Estates Representative - Richard Thomas
Design Team Rep's - As Required
Cost Manager - Will Eccles
Optional
Project Progress / Design Team Meeting | Monthly | Project Team (Technical) Forum - Detailed review of overall progress, brief, design and specification, planning, cost, risk, procurement, quality, logistics and H&S. |  |  |  | External Project Manager or Lead Design Consultant | Minutes and Task Log | External Project Manager Report Consultant Design Reports Consultant Cost Report Risk Register | External PM Design Team QS External PM
Staheholder Engagement - Design & Specification Sessions | As Required | Sustainability |  |  |  | Internal PM | Notes by Exception | Relevent Design & Specification (Scope of Work) Information Master Programme (Inc Decant Strategy)
Student Union / Student Services
IT & AV
UoL Estates & Maintenance
Catering
Security & Access Control etc
Fire Strategy
FF&E
Other
Contractor Progress Meetings (ONCE PRINCIPAL CONTRACTOR APPOINTED) | Monthly (minimum) | Review progress of construction/site activity, programme, quality, compliance, contract administration, statutory obligations, health & safety, cost, risk, handover etc. |  |  |  | External Project Manager | Minutes and Task Log | Contractor Progress Report | Principal Contractor
Weekly Site Walk | Bi-Weekly (minimum) | Regular 'informal' site walk to review general progress, consider short-term look ahead of activities, issues/risks and general quality of works. |  |  |  | Principal Contractor - Contracts/Project Manager | Notes by Exception | Short-Term Look Ahead Programme (4 weekly) | Principal Contractor